## Berita Acara
BERITA ACARA PEMAKAIAN ALAT BERAT
|  | BA No. | : 003/HTG-BASTB/VI/2019
|  | Project | : PT. Servo Lintas Raya
|  | Contract No. | : 4760000960
|  | Periode | : JUNI 2019
Pada hari Senin tanggal 08 Juli tahun 2019 dibuat berita acara tentang pemakaian (rental) alat berat milik PT. Harapan Tri Guna yang digunakan di Hauling Road milik PT. SPT. Servo Lintas Raya pada Periode Bulan JUNI 2019.
Dengan Keterangan pemakaian unit sebagai berikut :
No | Plant Data |  | Plant Hours | [7 empty] | Standard Availability | MA (%) | PA (%)
| Description | Code No. | Summary Hours |  | Schduled hours | Category
|  |  | Start | End |  | Opr | Down | No Oprt | Stby | TOTAL
1 | VIBRO DYNAPAC | WA 01 | 2399 | 2739 | 479 | 341 | 0 | 0 | 138 | 479 | 85% | 100% | 100%
2 | GRADER HIDROMEK | WA 02 | 3761 | 4090 | 449 | 329 | 0 | 0 | 120 | 449 | 85% | 100% | 100%
TOTAL |  |  |  |  | 928 | 670 | 0 | 0 | 258 | 928 | 85% | 100% | 100%
| Mech. Availability : | Opr | [5 empty] | MA | : Mechanical Availability
|  | Opr + Down | [5 empty] | PA | : Physical Availability
[8 empty] | Opr | : Total Operating Hours
| Phys. Availability : | Opr + Stby | [5 empty] | Down | : Total Downtime Hours
|  | Schduled Hours | [5 empty] | No Oprt | : Total No Operator Hours
[8 empty] | Stby | : Total Standby Hours
| Prepared By, | [5 empty] | Approved By,
| PT. HARAPAN TRI GUNA | [5 empty] | PT. SERVO LINTAS RAYA
| HENDRA TEDI GUNAWAN | [5 empty] | BUDI SANTOSO |  |  | HARY DAVID SUKMANA |  |  | HERU SASONGKO
[7 empty] | SPT OPERATION |  |  | MANAGER OPERATION |  |  | GM OPERATION

## WA 01
PT. SERVO LINTAS RAYA
DISTRIK MUARA ENIM
Monthly Monitoring Operation Unit at Intermediate Stockpile & Road Maintenance
Service Meter Reading
[10 empty] | Machine | VIBRO DYNAPAC | [7 empty] | From Hm : | 2399
MONTH: | [9 empty] | Serial Number | [8 empty] | To Hm : | 2739
JUNI 2019 | [9 empty] | Unit No | WA 01 | [7 empty] | Run Hm : | 340
From 01 Juni - 30 Juni 2019
Date | Plan | Day | [5 empty] | Remaks | Night | [5 empty] | Remaks | TOTAL | [5 empty] | PA | Daily Cummulative | Consumption Hours (Ltr/Hm) | 104 | 107 | Gen
|  | Start | Finish | Opr | BD | No Oprt | STB Hours |  | Start | Finish | Opr | BD | No Oprt | STB Hours |  | Start | Finish | Opr | BD | No Oprt | STB Hours | %
1 | 22 | 2399 | 2408 | 9 |  |  | 2 | PEMADATAN STOCK FILE 107 |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 2399 | 0 | 9 | 0 | 0 | 13 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
2 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
3 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
4 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
5 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
6 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
7 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
8 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
9 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
10 | 22 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0% | #REF! | 0 | #REF! | #REF! | #REF!
11 | 23 | 2408 | 2418 | 10 |  |  | 1 | PEMADATAN STOCK FILE 106 |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 2408 | 0 | 10 | 0 | 0 | 12 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
12 | 22 | 2418 | 2428 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 |  |  | 0 |  |  | 0 | STANDBY | 2418 | 0 | 10 | 0 | 0 | 12 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
13 | 22 | 2428 | 2438 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2438 | 2448 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2428 | 2448 | 20 | 0 | 0 | 2 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
14 | 22 | 2448 | 2458 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2458 | 2462 | 4 |  |  | 7 | PEMADATAN STOCK FILE 107 | 2448 | 2462 | 14 | 0 | 0 | 8 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
15 | 22 | 2462 | 2470 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2470 | 2477 | 7 |  |  | 4 | PEMADATAN STOCK FILE 107 | 2462 | 2477 | 15 | 0 | 0 | 7 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
16 |  | 2477 | 2485 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2485 | 2492 | 7 |  |  | 4 | PEMADATAN STOCK FILE 107 | 2477 | 1688 | 15 | 0 | 0 | 7 | 100%
17 |  | 2492 | 2501 | 9 |  |  | 2 | PEMADATAN STOCK FILE 107 | 2500 | 2508 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2492 | 2508 | 17 | 0 | 0 | 5 | 100%
18 |  | 2508 | 2517 | 9 |  |  | 2 | PEMADATAN STOCK FILE 107 | 2517 | 2525 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2508 | 2525 | 17 | 0 | 0 | 22 | 100%
19 |  | 2525 | 2534 | 9 |  |  | 2 | PEMADATAN STOCK FILE 107 | 2534 | 2537 | 3 |  |  | 8 | PEMADATAN STOCK FILE 107 | 2525 | 1723 | 12 | 0 | 0 | 10 | 100%
20 |  | 2537 | 2547 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2547 | 2556 | 9 |  |  | 2 | PEMADATAN STOCK FILE 107 | 2537 | 1730 | 19 | 0 | 0 | 3 | 100%
21 |  | 2556 | 2565 | 9 |  |  | 2 | PEMADATAN STOCK FILE 107 | 2565 | 2573 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2556 | 1739 | 17 | 0 | 0 | 5 | 100%
22 |  | 2573 | 2583 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2583 | 2593 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2573 | 1745 | 20 | 0 | 0 | 2 | 100%
23 |  | 2593 | 2603 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2603 | 2613 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2593 | 1751 | 20 | 0 | 0 | 2 | 100%
24 |  | 2613 | 2623 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2623 | 2633 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2613 | 2633 | 20 | 0 | 0 | 2 | 100%
25 |  | 2633 | 2643 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2643 | 2653 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2633 | 1781 | 20 | 0 | 0 | 2 | 100%
26 |  | 2653 | 2661 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2661 | 2671 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2653 | 2671 | 18 | 0 | 0 | 4 | 100%
27 | 22 | 2671 | 2679 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2679 | 2687 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2671 | 2687 | 16 | 0 | 0 | 6 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
28 | 22 | 2687 | 2695 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2695 | 2703 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2687 | 2703 | 16 | 0 | 0 | 6 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
29 | 22 | 2703 | 2711 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2711 | 2721 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2703 | 2721 | 18 | 0 | 0 | 4 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
30 |  | 2721 | 2731 | 10 |  |  | 1 | PEMADATAN STOCK FILE 107 | 2731 | 2739 | 8 |  |  | 3 | PEMADATAN STOCK FILE 107 | 2721 | 2739 | 18 | 0 | 0 | 4 | 100%
|  |  |  | O-Hrs | BD | No Oprt | STB |  |  |  | O-Hrs | BD | No Oprt | STB |  |  |  | O-Hrs | BD | No Oprt | STB |  | Cummulative |  | #REF! | #REF! | #REF!
|  | TOTAL |  | 193 | 0 | 0 | 38 |  | TOTAL |  | 148 | 0 | 0 | 50 |  | TOTAL |  | 341 | 0 | 0 | 138 |  |  | #REF!
[18 empty] | 341 | 0 | 0 | 88
[15 empty] | Schedule |  | S |  | Physical Availability
[15 empty] | Hours | Active | Schedule HRS
[15 empty] | DAILY | Days | THIS MONTH |  | S - UM - SM = | 479 | = | 100%
[15 empty] | 22 | 30 | 660 |  | S | 479
|  |  |  | PT. HARAPAN TRI GUNA | [10 empty] | PT. SERVO LINTAS RAYA
|  |  |  | HENDRA TEDI GUNAWAN | [10 empty] | Nursilawati |  |  |  | Budi Santoso
[15 empty] | Data Control |  |  |  | Spt. Operation
Avg Fuel = Lts/SMR
Avg Fuel = Lts/SMR

## WA 02
PT. SERVO LINTAS RAYA
DISTRIK MUARA ENIM
Monthly Monitoring Operation Unit at Intermediate Stockpile & Road Maintenance
Service Meter Reading
[10 empty] | Machine | GRADER HIDROMEK | [7 empty] | From Hm : | 3761
MONTH: | [9 empty] | Serial Number | [8 empty] | To Hm : | 4090
JUNI 2019 | [9 empty] | Unit No | WA 02 | [7 empty] | Run Hm : | 329
From 01 Juni - 30 Juni 2019
Date | Plan | Day | [5 empty] | Remaks | Night | [5 empty] | Remaks | TOTAL | [5 empty] | PA | Daily Cummulative | Consumption Hours (Ltr/Hm) | 104 | 107 | Gen
|  | Start | Finish | Opr | BD | No Oprt | STB Hours |  | Start | Finish | Opr | BD | No Oprt | STB Hours |  | Start | Finish | Opr | BD | No Oprt | STB Hours | %
1 | 22 | 3761 | 3770 | 9 |  |  | 2 | GREADING STOCK PILE 107 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 3761 | 0 | 9 | 0 | 0 | 13 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
2 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
3 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
4 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
5 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
6 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
7 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
8 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
9 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
10 |  |  |  | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 0 | 0 | 0 | 0 | 0 |  | 0%
11 |  | 3769 | 3779 | 10 |  |  | 1 | MENGHAMPAR TANAH 113 | 0 | 0 | 0 |  |  | 0 | LIBUR LEBARAN | 3769 | 0 | 10 | 0 | 0 | 12 | 100%
12 |  | 3779 | 3787 | 8 |  |  | 3 | PEMBENAHAN JALAN STOCK PILE 107 | 3787 | 0 | 0 |  |  | 0 | STANDBY | 3779 | 0 | 8 | 0 | 0 | 14 | 100%
13 |  | 3787 | 3795 | 8 |  |  | 3 | PEMBENAHAN JALAN STOCK PILE 107 | 3795 | 3803 | 8 |  |  | 3 | GREDING AKSES STOCK PILE 107 | 3787 | 3803 | 16 | 0 | 0 | 6 | 100%
14 |  | 3803 | 3810 | 7 |  |  | 4 | PEMBENAHAN JALAN STOCK PILE 107 | 3810 | 3819 | 9 |  |  | 2 | GREDING AKSES STOCK PILE 107 | 3803 | 3819 | 16 | 0 | 0 | 6 | 100%
15 | 22 | 3819 | 3826 | 7 |  |  | 4 | PEMBENAHAN JALAN STOCK PILE 107 | 3826 | 3835 | 9 |  |  | 2 | GREDING AKSES STOCK PILE 107 | 3819 | 3835 | 16 | 0 | 0 | 6 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
16 | 22 | 3735 | 3743 | 8 |  |  | 3 | PEMBENAHAN JALAN STOCK PILE 107 | 3843 | 3851 | 8 |  |  | 3 | GREDING AKSES STOCK PILE 107 | 3735 | 2953 | 16 | 0 | 0 | 6 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
17 | 22 | 3851 | 3859 | 8 |  |  | 3 | PEMBENAHAN JALAN STOCK PILE 107 | 3859 | 3868 | 9 |  |  | 2 | GREDING AKSES STOCK PILE 107 | 3851 | 3868 | 17 | 0 | 0 | 5 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
18 | 22 | 3868 | 3878 | 10 |  |  | 1 | GREADING AKSES ROAD KM 107 | 3878 | 3885 | 7 |  |  | 4 | GREDING AKSES STOCK PILE 107 | 3868 | 3885 | 17 | 0 | 0 | 5 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
19 | 22 | 3885 | 3895 | 10 |  |  | 1 | GREADING AKSES ROAD KM 107 | 3895 | 3902 | 7 |  |  | 0 | GREDING AKSES STOCK PILE 107 | 3885 | 3902 | 17 | 0 | 0 | 5 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
20 | 22 | 3902 | 3912 | 10 |  |  | 1 | GREADING STOCK PILE 107 | 3912 | 3920 | 8 |  |  | 0 | GREDING AKSES STOCK PILE 107 | 3902 | 3920 | 18 | 0 | 0 | 4 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
21 | 22 | 3920 | 3930 | 10 |  |  | 1 | GREADING STOCK PILE 107 | 3930 | 3938 | 8 |  |  | 3 | GREADING ACC ROAD STOCK PILE 107 | 3920 | 3938 | 18 | 0 | 0 | 4 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
22 | 22 | 3938 | 3947 | 9 |  |  | 2 | GREADING STOCK PILE 107 | 3947 | 3955 | 8 |  |  | 3 | GREADING ACC ROAD STOCK PILE 107 | 3938 | 3955 | 17 | 0 | 0 | 5 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
23 | 22 | 3955 | 3963 | 8 |  |  | 3 | GREADING STOCK PILE 107 | 3963 | 3973 | 10 |  |  | 1 | GREADING ACC ROAD STOCK PILE 107 | 3955 | 3973 | 18 | 0 | 0 | 4 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
24 | 23 | 3973 | 3982 | 9 |  |  | 2 | GREADING STOCK PILE 107 | 3982 | 3992 | 10 |  |  | 1 | SKRIPING STOCK PILE 107 | 3973 | 3992 | 19 | 0 | 0 | 3 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
25 | 22 | 3992 | 4001 | 9 |  |  | 2 | GREADING STOCK PILE 107 | 4001 | 4010 | 9 |  |  | 2 | GREADING ACC ROAD STOCK PILE 107 | 3992 | 4010 | 18 | 0 | 0 | 4 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
26 | 22 | 4010 | 4019 | 9 |  |  | 2 | GREADING STOCK PILE 107 | 4019 | 4028 | 9 |  |  | 2 | GREADING ACC ROAD STOCK PILE 107 | 4010 | 4028 | 18 | 0 | 0 | 4 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
27 | 22 | 4028 | 4036 | 8 |  |  | 3 | GREADING STOCK PILE 107 | 4036 | 4045 | 9 |  |  | 2 | GREADING ACC ROAD STOCK PILE 107 | 4028 | 4045 | 17 | 0 | 0 | 5 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
28 | 22 | 4045 | 4053 | 8 |  |  | 3 | GREADING STOCK PILE 107 | 4054 | 4063 | 9 |  |  | 2 | GREADING ACC ROAD STOCK PILE 107 | 4045 | 4063 | 17 | 0 | 0 | 5 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
29 | 22 | 4062 | 4071 | 9 |  |  | 2 | GREADING STOCK PILE 107 | 4072 | 4081 | 9 |  |  | 2 | GREADING ACC ROAD STOCK PILE 107 | 4062 | 4081 | 18 | 0 | 0 | 4 | 100% | #REF! | 0 | #REF! | #REF! | #REF!
30 |  | 0 | 0 | 0 |  |  | 0 | BREAK DOWN/SERVICE | 4081 | 4090 | 9 |  |  | 2 | GREADING ACC ROAD STOCK PILE 107 | 0 | 4090 | 9 | 0 | 0 |  | 0%
|  |  |  | O-Hrs | BD | No Oprt | STB |  |  |  | O-Hrs | BD | No Oprt | STB |  |  |  | O-Hrs | BD | No Oprt | STB |  | Cummulative |  | #REF! | #REF! | #REF!
|  | TOTAL |  | 174 | 0 | 0 | 46 |  | TOTAL |  | 155 | 0 | 0 | 26 |  | TOTAL |  | 329 | 0 | 0 | 120 |  |  | #REF!
[18 empty] | 329 | 0 | 0 | 72
[15 empty] | Schedule |  | S |  | Physical Availability
[15 empty] | Hours | Active | Schedule HRS
[15 empty] | DAILY | Days | THIS MONTH |  | S - UM - SM = | 449 | = | 100%
[15 empty] | 22 | 30 | 660 |  | S | 449
|  |  |  | PT. HARAPAN TRI GUNA | [10 empty] | PT. SERVO LINTAS RAYA
|  |  |  | HENDRA TEDI GUNAWAN | [10 empty] | Nursilawati |  |  |  | Budi Santoso
[15 empty] | Data Control |  |  |  | Spt. Operation
Avg Fuel = Lts/SMR
Avg Fuel = Lts/SMR